## Dashboard
PROJECT OPERATIONS ¦ GITHUB SNAPSHOT
13.10.2026 · Smart Garden, данные только для чтения · не финансовая отчётность
ISSUES | Количество | PULL REQUESTS | Количество
Всего Issues | 137 | Всего PR | 95
Закрыто | 118 | Merged | 88
Открыто | 19 | Open | 5
Доля закрытых | 86.13% | Closed (no merge) | 2
ЧТО НЕЛЬЗЯ ЗАКЛЮЧИТЬ ИЗ ЭТИХ ДАННЫХ
Доля закрытых Issues НЕ равна готовности проекта. Нет плана сроков, бюджета, часов, story points и подтверждённых затрат: SPI/CPI, velocity и выполнение плана здесь не рассчитываются.
Источники и воспроизводимость
Issues и PRs · публичный REST API GitHub · дата среза 13.10.2026
Все объекты имеют source_url. Pull Requests исключены из Issues.
Методика — docs/ANALYSIS_METHOD.md; тесты — python -m unittest discover -s tests -v
Управленческие вопросы: персональные данные (#223), пилот (#187), универсальные профили (#162), PWA (#189).
ЕЖЕДНЕВНАЯ АКТИВНОСТЬ · реальный снимок GitHub API

## Issues
issue_number | created_date | closed_date | state | assignee | title_if_recorded | source_url
1 | 2026-09-23 | 2026-09-25 | closed | F1zname | SHARED-01 — Зафиксировать API Contract v0.1 | https://github.com/ONN9IX/smart-garden/issues/1
2 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/2
3 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/3
4 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/4
5 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/5
6 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/6
7 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/7
8 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/8
9 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/9
10 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/10
11 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/11
12 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/12
13 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/13
14 | 2026-09-23 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/14
15 | 2026-09-23 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/15
16 | 2026-09-23 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/16
17 | 2026-09-23 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/17
18 | 2026-09-23 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/18
19 | 2026-09-23 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/19
20 | 2026-09-23 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/20
21 | 2026-09-23 | 2026-09-23 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/21
22 | 2026-09-23 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/22
23 | 2026-09-23 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/23
24 | 2026-09-23 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/24
25 | 2026-09-23 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/25
26 | 2026-09-23 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/26
27 | 2026-09-23 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/27
28 | 2026-09-23 | 2026-09-23 | closed | ONN9IX | REPO-01 — Включить защиту main перед первым merge | https://github.com/ONN9IX/smart-garden/issues/28
32 | 2026-09-25 | 2026-09-29 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/32
33 | 2026-09-25 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/33
34 | 2026-09-25 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/34
37 | 2026-09-25 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/37
38 | 2026-09-25 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/38
39 | 2026-09-25 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/39
40 | 2026-09-25 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/40
41 | 2026-09-25 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/41
42 | 2026-09-25 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/42
43 | 2026-09-25 | 2026-09-25 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/43
44 | 2026-09-25 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/44
45 | 2026-09-25 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/45
46 | 2026-09-25 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/46
47 | 2026-09-25 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/47
48 | 2026-09-25 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/48
49 | 2026-09-25 | 2026-09-25 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/49
50 | 2026-09-25 | 2026-09-26 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/50
51 | 2026-09-25 | 2026-09-26 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/51
52 | 2026-09-25 | 2026-09-26 | closed | ONN9IX | STAGE2-00 — Порядок разработки и контроль Stage 2 | https://github.com/ONN9IX/smart-garden/issues/52
68 | 2026-09-26 | 2026-09-26 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/68
70 | 2026-09-26 | 2026-09-26 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/70
72 | 2026-09-26 | 2026-09-26 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/72
74 | 2026-09-26 | 2026-09-26 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/74
76 | 2026-09-26 | 2026-09-26 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/76
78 | 2026-09-26 | 2026-09-26 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/78
80 | 2026-09-26 | 2026-09-26 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/80
82 | 2026-09-26 | 2026-09-26 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/82
84 | 2026-09-26 | 2026-09-26 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/84
86 | 2026-09-26 | 2026-09-27 | closed |  | STAGE3-ACCEPTANCE — финальная приёмка и freeze Stage 3 | https://github.com/ONN9IX/smart-garden/issues/86
87 | 2026-09-26 | 2026-09-26 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/87
88 | 2026-09-26 | 2026-09-26 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/88
94 | 2026-09-27 | 2026-09-28 | closed |  | STAGE4-AUDIT — immutable business audit vertical slice | https://github.com/ONN9IX/smart-garden/issues/94
95 | 2026-09-27 | 2026-09-28 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/95
98 | 2026-09-28 | 2026-09-28 | closed |  | STAGE4-ACCEPTANCE — финальная приёмка и freeze Stage 4 | https://github.com/ONN9IX/smart-garden/issues/98
99 | 2026-09-28 | 2026-09-28 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/99
102 | 2026-09-28 | 2026-09-29 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/102
103 | 2026-09-28 | 2026-09-29 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/103
106 | 2026-09-29 | 2026-09-29 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/106
107 | 2026-09-29 | 2026-09-29 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/107
108 | 2026-09-29 | 2026-09-29 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/108
112 | 2026-09-29 | 2026-09-29 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/112
114 | 2026-09-29 | 2026-09-29 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/114
115 | 2026-09-29 | 2026-09-29 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/115
117 | 2026-09-29 | 2026-09-29 | closed | F1zname | STAGE5-ACCEPTANCE — final technical acceptance and freeze | https://github.com/ONN9IX/smart-garden/issues/117
119 | 2026-09-29 | 2026-09-29 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/119
121 | 2026-09-30 | 2026-09-30 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/121
123 | 2026-09-30 | 2026-09-30 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/123
124 | 2026-09-30 | 2026-09-30 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/124
126 | 2026-09-30 | 2026-09-30 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/126
129 | 2026-09-30 | 2026-09-30 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/129
131 | 2026-09-30 | 2026-10-01 | closed | F1zname |  | https://github.com/ONN9IX/smart-garden/issues/131
132 | 2026-09-30 | 2026-09-30 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/132
133 | 2026-09-30 | 2026-09-30 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/133
135 | 2026-09-30 | 2026-09-30 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/135
137 | 2026-09-30 | 2026-09-30 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/137
139 | 2026-09-30 | 2026-09-30 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/139
142 | 2026-10-01 | 2026-10-01 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/142
144 | 2026-10-01 | 2026-10-01 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/144
146 | 2026-10-01 | 2026-10-01 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/146
148 | 2026-10-01 | 2026-10-01 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/148
150 | 2026-10-01 | 2026-10-01 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/150
152 | 2026-10-01 | 2026-10-01 | closed | ONN9IX | S6-ACCEPTANCE — integrated four-role acceptance and product freeze | https://github.com/ONN9IX/smart-garden/issues/152
154 | 2026-10-01 | 2026-10-01 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/154
156 | 2026-10-01 | 2026-10-01 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/156
158 | 2026-10-01 | 2026-10-07 | closed | ONN9IX | MANUAL-ACCEPTANCE — three-device MVP verification | https://github.com/ONN9IX/smart-garden/issues/158
159 | 2026-10-02 | 2026-10-02 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/159
161 | 2026-10-05 |  | open | ONN9IX | INTEGRATIONS-DESIGN — Bitrix24 / external CRM architecture | https://github.com/ONN9IX/smart-garden/issues/161
162 | 2026-10-05 |  | open | ONN9IX | CORE-01 — универсальные профили KINDERGARTEN / GYMNASTICS (ПРОМАКС 2.0) | https://github.com/ONN9IX/smart-garden/issues/162
163 | 2026-10-06 | 2026-10-06 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/163
164 | 2026-10-06 | 2026-10-07 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/164
166 | 2026-10-06 | 2026-10-06 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/166
168 | 2026-10-06 | 2026-10-06 | closed | ONN9IX |  | https://github.com/ONN9IX/smart-garden/issues/168
170 | 2026-10-06 |  | open | ONN9IX | PLATFORM-LIFECYCLE — runtime and dependency upgrade guardrails | https://github.com/ONN9IX/smart-garden/issues/170
171 | 2026-10-06 |  | open |  | PEOPLE-UX-DESIGN — DIRECTOR v2 people, groups and person profiles | https://github.com/ONN9IX/smart-garden/issues/171
172 | 2026-10-07 | 2026-10-07 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/172
173 | 2026-10-07 | 2026-10-07 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/173
174 | 2026-10-07 | 2026-10-08 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/174
175 | 2026-10-07 | 2026-10-08 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/175
176 | 2026-10-07 | 2026-10-07 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/176
177 | 2026-10-07 | 2026-10-12 | closed | F1zname | DIRECTOR-V2-E — control, notifications, journal and settings | https://github.com/ONN9IX/smart-garden/issues/177
178 | 2026-10-07 |  | open |  |  | https://github.com/ONN9IX/smart-garden/issues/178
179 | 2026-10-07 | 2026-10-07 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/179
183 | 2026-10-07 | 2026-10-08 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/183
185 | 2026-10-08 | 2026-10-08 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/185
187 | 2026-10-08 |  | open |  | PILOT-PREP — kindergarten synthetic demo, buyer discovery and 152-FZ go/no-go | https://github.com/ONN9IX/smart-garden/issues/187
189 | 2026-10-08 |  | open |  | MOBILE-PWA-DESIGN — installable ПРОМАКС app first, native distribution later | https://github.com/ONN9IX/smart-garden/issues/189
190 | 2026-10-08 |  | open |  |  | https://github.com/ONN9IX/smart-garden/issues/190
195 | 2026-10-08 | 2026-10-09 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/195
197 | 2026-10-08 |  | open |  | PARENT-ATTENDANCE-ALERTS — automatic arrival/departure events and parent preferences | https://github.com/ONN9IX/smart-garden/issues/197
198 | 2026-10-08 |  | open |  | TASK-DETAILS — editing, notes and change notifications | https://github.com/ONN9IX/smart-garden/issues/198
199 | 2026-10-08 |  | open |  | DIRECT-MESSAGING-V3 — authorized Director and Teacher recipient chooser | https://github.com/ONN9IX/smart-garden/issues/199
200 | 2026-10-08 |  | open |  | GARDEN-EVENTS — scoped calendar events, audiences and notifications | https://github.com/ONN9IX/smart-garden/issues/200
201 | 2026-10-08 | 2026-10-12 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/201
202 | 2026-10-08 | 2026-10-12 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/202
203 | 2026-10-08 | 2026-10-08 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/203
204 | 2026-10-08 |  | open | ONN9IX | INFRA: gated n8n + Codex + GitHub Actions + Telegram automation pilot | https://github.com/ONN9IX/smart-garden/issues/204
207 | 2026-10-09 |  | open |  | INFRA-WINDOWS-CODEX — secure local dispatcher, approval gate and autonomous PR repair | https://github.com/ONN9IX/smart-garden/issues/207
209 | 2026-10-09 |  | open |  | INFRA-WINDOWS-SECURITY — isolated controller/worker/publisher and witnessed activation gate | https://github.com/ONN9IX/smart-garden/issues/209
211 | 2026-10-10 | 2026-10-10 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/211
213 | 2026-10-10 |  | open |  | SAM-1 — Safe Automatic Merge architecture decision (inactive, NO-GO) | https://github.com/ONN9IX/smart-garden/issues/213
214 | 2026-10-10 | 2026-10-10 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/214
216 | 2026-10-10 | 2026-10-10 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/216
218 | 2026-10-11 |  | open |  | INFRA-DISPATCH — Master Chat → Codex Cloud запуск Issue без платного API (feasibility) | https://github.com/ONN9IX/smart-garden/issues/218
221 | 2026-10-12 | 2026-10-12 | closed | ONN9IX | PLATFORM-OWNER-MVP — secure operator cabinet, kindergarten onboarding and director bootstrap | https://github.com/ONN9IX/smart-garden/issues/221
222 | 2026-10-12 |  | open |  | LEAN-ROADMAP — ПРОМАКС 2.0: кабинеты → универсальные профили → PWA → проверка спроса | https://github.com/ONN9IX/smart-garden/issues/222
223 | 2026-10-12 |  | open |  | PRIVACY-152FZ — public policy, role-specific notices and purpose-bound consent registry | https://github.com/ONN9IX/smart-garden/issues/223
224 | 2026-10-12 | 2026-10-12 | closed |  |  | https://github.com/ONN9IX/smart-garden/issues/224
226 | 2026-10-12 | 2026-10-13 | closed |  | DIRECTOR-REDESIGN-V3 — единый оперативный кабинет, группы, дети и контроль | https://github.com/ONN9IX/smart-garden/issues/226
228 | 2026-10-12 | 2026-10-12 | closed | ONN9IX | DOCS — актуализировать README по интегрированному ПРОМАКС и baseline после #225 | https://github.com/ONN9IX/smart-garden/issues/228

## PRs
pr_number | created_date | merged_date | outcome | source_url
29 | 2026-09-23 |  | closed_not_merged | https://github.com/ONN9IX/smart-garden/pull/29
30 | 2026-09-23 |  | closed_not_merged | https://github.com/ONN9IX/smart-garden/pull/30
31 | 2026-09-24 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/31
35 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/35
36 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/36
53 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/53
54 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/54
55 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/55
56 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/56
57 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/57
58 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/58
59 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/59
60 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/60
61 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/61
62 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/62
63 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/63
64 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/64
65 | 2026-09-25 | 2026-09-25 | merged | https://github.com/ONN9IX/smart-garden/pull/65
66 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/66
67 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/67
69 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/69
71 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/71
73 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/73
75 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/75
77 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/77
79 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/79
81 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/81
83 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/83
85 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/85
89 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/89
90 | 2026-09-26 | 2026-09-26 | merged | https://github.com/ONN9IX/smart-garden/pull/90
91 | 2026-09-27 | 2026-09-27 | merged | https://github.com/ONN9IX/smart-garden/pull/91
92 | 2026-09-27 | 2026-09-27 | merged | https://github.com/ONN9IX/smart-garden/pull/92
93 | 2026-09-27 | 2026-09-27 | merged | https://github.com/ONN9IX/smart-garden/pull/93
96 | 2026-09-27 | 2026-09-28 | merged | https://github.com/ONN9IX/smart-garden/pull/96
97 | 2026-09-28 | 2026-09-28 | merged | https://github.com/ONN9IX/smart-garden/pull/97
100 | 2026-09-28 | 2026-09-28 | merged | https://github.com/ONN9IX/smart-garden/pull/100
101 | 2026-09-28 | 2026-09-28 | merged | https://github.com/ONN9IX/smart-garden/pull/101
104 | 2026-09-28 | 2026-09-29 | merged | https://github.com/ONN9IX/smart-garden/pull/104
105 | 2026-09-29 | 2026-09-29 | merged | https://github.com/ONN9IX/smart-garden/pull/105
109 | 2026-09-29 | 2026-09-29 | merged | https://github.com/ONN9IX/smart-garden/pull/109
110 | 2026-09-29 | 2026-09-29 | merged | https://github.com/ONN9IX/smart-garden/pull/110
111 | 2026-09-29 | 2026-09-29 | merged | https://github.com/ONN9IX/smart-garden/pull/111
113 | 2026-09-29 | 2026-09-29 | merged | https://github.com/ONN9IX/smart-garden/pull/113
116 | 2026-09-29 | 2026-09-29 | merged | https://github.com/ONN9IX/smart-garden/pull/116
118 | 2026-09-29 | 2026-09-29 | merged | https://github.com/ONN9IX/smart-garden/pull/118
120 | 2026-09-29 | 2026-09-29 | merged | https://github.com/ONN9IX/smart-garden/pull/120
122 | 2026-09-30 | 2026-09-30 | merged | https://github.com/ONN9IX/smart-garden/pull/122
125 | 2026-09-30 | 2026-09-30 | merged | https://github.com/ONN9IX/smart-garden/pull/125
127 | 2026-09-30 | 2026-09-30 | merged | https://github.com/ONN9IX/smart-garden/pull/127
128 | 2026-09-30 | 2026-09-30 | merged | https://github.com/ONN9IX/smart-garden/pull/128
130 | 2026-09-30 | 2026-09-30 | merged | https://github.com/ONN9IX/smart-garden/pull/130
134 | 2026-09-30 | 2026-09-30 | merged | https://github.com/ONN9IX/smart-garden/pull/134
136 | 2026-09-30 | 2026-09-30 | merged | https://github.com/ONN9IX/smart-garden/pull/136
138 | 2026-09-30 | 2026-09-30 | merged | https://github.com/ONN9IX/smart-garden/pull/138
140 | 2026-09-30 | 2026-09-30 | merged | https://github.com/ONN9IX/smart-garden/pull/140
141 | 2026-10-01 | 2026-10-01 | merged | https://github.com/ONN9IX/smart-garden/pull/141
143 | 2026-10-01 | 2026-10-01 | merged | https://github.com/ONN9IX/smart-garden/pull/143
145 | 2026-10-01 | 2026-10-01 | merged | https://github.com/ONN9IX/smart-garden/pull/145
147 | 2026-10-01 | 2026-10-01 | merged | https://github.com/ONN9IX/smart-garden/pull/147
149 | 2026-10-01 | 2026-10-01 | merged | https://github.com/ONN9IX/smart-garden/pull/149
151 | 2026-10-01 | 2026-10-01 | merged | https://github.com/ONN9IX/smart-garden/pull/151
153 | 2026-10-01 | 2026-10-01 | merged | https://github.com/ONN9IX/smart-garden/pull/153
155 | 2026-10-01 | 2026-10-01 | merged | https://github.com/ONN9IX/smart-garden/pull/155
157 | 2026-10-01 | 2026-10-01 | merged | https://github.com/ONN9IX/smart-garden/pull/157
160 | 2026-10-02 | 2026-10-02 | merged | https://github.com/ONN9IX/smart-garden/pull/160
165 | 2026-10-06 | 2026-10-06 | merged | https://github.com/ONN9IX/smart-garden/pull/165
167 | 2026-10-06 | 2026-10-06 | merged | https://github.com/ONN9IX/smart-garden/pull/167
169 | 2026-10-06 | 2026-10-06 | merged | https://github.com/ONN9IX/smart-garden/pull/169
180 | 2026-10-07 | 2026-10-07 | merged | https://github.com/ONN9IX/smart-garden/pull/180
181 | 2026-10-07 | 2026-10-07 | merged | https://github.com/ONN9IX/smart-garden/pull/181
182 | 2026-10-07 | 2026-10-07 | merged | https://github.com/ONN9IX/smart-garden/pull/182
184 | 2026-10-07 | 2026-10-08 | merged | https://github.com/ONN9IX/smart-garden/pull/184
186 | 2026-10-08 | 2026-10-08 | merged | https://github.com/ONN9IX/smart-garden/pull/186
188 | 2026-10-08 | 2026-10-08 | merged | https://github.com/ONN9IX/smart-garden/pull/188
191 | 2026-10-08 |  | open | https://github.com/ONN9IX/smart-garden/pull/191
192 | 2026-10-08 |  | open | https://github.com/ONN9IX/smart-garden/pull/192
193 | 2026-10-08 |  | open | https://github.com/ONN9IX/smart-garden/pull/193
194 | 2026-10-08 |  | open | https://github.com/ONN9IX/smart-garden/pull/194
196 | 2026-10-08 | 2026-10-08 | merged | https://github.com/ONN9IX/smart-garden/pull/196
205 | 2026-10-08 | 2026-10-08 | merged | https://github.com/ONN9IX/smart-garden/pull/205
206 | 2026-10-08 | 2026-10-09 | merged | https://github.com/ONN9IX/smart-garden/pull/206
208 | 2026-10-09 | 2026-10-09 | merged | https://github.com/ONN9IX/smart-garden/pull/208
210 | 2026-10-09 | 2026-10-09 | merged | https://github.com/ONN9IX/smart-garden/pull/210
212 | 2026-10-10 | 2026-10-10 | merged | https://github.com/ONN9IX/smart-garden/pull/212
215 | 2026-10-10 | 2026-10-10 | merged | https://github.com/ONN9IX/smart-garden/pull/215
217 | 2026-10-10 | 2026-10-10 | merged | https://github.com/ONN9IX/smart-garden/pull/217
219 | 2026-10-11 | 2026-10-12 | merged | https://github.com/ONN9IX/smart-garden/pull/219
220 | 2026-10-12 | 2026-10-12 | merged | https://github.com/ONN9IX/smart-garden/pull/220
225 | 2026-10-12 | 2026-10-12 | merged | https://github.com/ONN9IX/smart-garden/pull/225
227 | 2026-10-12 | 2026-10-12 | merged | https://github.com/ONN9IX/smart-garden/pull/227
229 | 2026-10-12 | 2026-10-12 | merged | https://github.com/ONN9IX/smart-garden/pull/229
230 | 2026-10-12 | 2026-10-12 | merged | https://github.com/ONN9IX/smart-garden/pull/230
231 | 2026-10-13 | 2026-10-13 | merged | https://github.com/ONN9IX/smart-garden/pull/231
232 | 2026-10-13 |  | open | https://github.com/ONN9IX/smart-garden/pull/232

## Daily Activity
date | issues_created | issues_closed | prs_created | prs_merged
2026-09-23 | 28 | 2 | 2 | 0
2026-09-24 | 0 | 0 | 1 | 0
2026-09-25 | 19 | 41 | 15 | 16
2026-09-26 | 12 | 14 | 13 | 13
2026-09-27 | 2 | 1 | 4 | 3
2026-09-28 | 4 | 4 | 4 | 4
2026-09-29 | 8 | 11 | 8 | 9
2026-09-30 | 11 | 10 | 9 | 9
2026-10-01 | 9 | 9 | 9 | 9
2026-10-02 | 1 | 1 | 1 | 1
2026-10-03 | 0 | 0 | 0 | 0
2026-10-04 | 0 | 0 | 0 | 0
2026-10-05 | 2 | 0 | 0 | 0
2026-10-06 | 6 | 3 | 3 | 3
2026-10-07 | 9 | 6 | 4 | 3
2026-10-08 | 13 | 5 | 9 | 5
2026-10-09 | 2 | 1 | 2 | 3
2026-10-10 | 4 | 3 | 3 | 3
2026-10-11 | 1 | 0 | 1 | 0
2026-10-12 | 6 | 6 | 5 | 6
2026-10-13 | 0 | 1 | 2 | 1

## Risks
risk_id | risk | probability_1_5 | impact_1_5 | assessment_status | source_issue | url | mitigation_proposal | risk_score
R-01 | Готовность процессов персональных данных | 3 | 5 | Экспертная учебная оценка | 223 | https://github.com/ONN9IX/smart-garden/issues/223 | Провести security и privacy go/no-go перед пилотом | 15
R-02 | Недостаточная проверка пилотных сценариев | 3 | 4 | Экспертная учебная оценка | 187 | https://github.com/ONN9IX/smart-garden/issues/187 | Утвердить критерии синтетического пилота | 12
R-03 | Расширение объёма работ универсальными профилями | 4 | 4 | Экспертная учебная оценка | 162 | https://github.com/ONN9IX/smart-garden/issues/162 | Разделить MVP и будущую архитектуру | 16
R-04 | Недоработанные мобильные сценарии | 3 | 3 | Экспертная учебная оценка | 189 | https://github.com/ONN9IX/smart-garden/issues/189 | Провести UX проверку устройств и PWA | 9
R-05 | Риски разрешений при автоматизации доставки | 3 | 5 | Экспертная учебная оценка | 204 | https://github.com/ONN9IX/smart-garden/issues/204 | Проверить approval gate и права публикации | 15

## Methodology
Показатель / правило | Пояснение
Дата среза | 13 октября 2026; это не live-отчёт
Источник | Публичные GitHub Issues и Pull Requests репозитория ONN9IX/smart-garden
Issues | Из общего endpoint /issues исключены записи с объектом pull_request
Закрытые Issues | state=closed, закрытие не означает готовность всего продукта
PR merged | merged_at != null, не путать с просто closed
Сроки | Календарные даты GitHub не равны человеко-часам
Бюджет / EVM | Не рассчитаны: нет PV, EV, AC и baseline
Риски | Вероятность/влияние — экспертные учебные оценки, не факты исходного проекта
ПДн | Технический MVP не равен production-ready для обработки реальных ПДн
Обновление | python scripts/refresh_from_github.py и затем build_reports.py; XLSX вручную обновить